## Action Plan
ACTION PLAN TEMPLATE
PROJECT NAME | PROJECT MANAGER
Startup Conference | John B.
INTERIM GOALS | ASSIGNED TO | PRIORITY | STATUS | START | END | NOTES
Goal #1: Select Venue
Identify venue options | Ron | High | Complete | 2019-03-08 | 2019-03-08
Visit venues | Ron | High | Complete | 2019-03-09 | 2019-03-11
Sign contract | Bella & Ron | High | In Progress | 2019-03-12 | 2019-03-12 | Contact finance department
Goal #2: Secure Speakers
Select speakers | Maria | High | Complete | 2019-03-08 | 2019-03-10
Recruit speakers | Dan | High | Complete | 2019-03-10 | 2019-03-14
Speaker bios | Bella | Medium | Not started | 2019-03-14 | 2019-03-14
Confirm speakers | Bella | High | Not started | 2019-03-14 | 2019-03-17 | Inform about this to Sponsors & Stakeholders
Goal #3: Secure Sponsors
Identify sponsors | Ron | High | In progress | 2019-03-12 | 2019-03-20
Write up sponsor agreement | Bella | High | In progress | 2019-03-12 | 2019-03-18
Send emails | Maria | High | In progress | 2019-03-13 | 2019-03-25
Make cold calls | Dan | High | In progress | 2019-03-13 | 2019-03-25 | From sales team
Goal #4: Promote event
Create banners | Rahul | Low | Complete | 2019-03-10 | 2019-03-12
Event Listing | Miley | Low | Complete | 2019-03-10 | 2019-03-12
Create social media strategy | Miley & Ross | Low | In progress | 2019-03-10 | 2019-03-13
Make marketing materials | Rahul | High | Not started | 2019-03-18 | 2019-03-25 | Posters, Fliers, Sponsor materials

## Action Plan Blank
ACTION PLAN TEMPLATE
PROJECT NAME | PROJECT MANAGER
INTERIM GOALS | ASSIGNED TO | PRIORITY | STATUS | START | END | NOTES
Goal #1:
Goal #2:
Goal #3:
Goal #4: